## Sheet1
Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central
Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
329544 | B3 - 1ST FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.010.003. | 0.0000 | Labour | 0 | 0.0000
332022 | B3 - 1ST FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.010.007. | 0.0000 | Labour | 0 | 0.0000
329547 | B3 - 2ND FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.011.003. | 0.0000 | Labour | 0 | 0.0000
332023 | B3 - 2ND FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.011.007. | 0.0000 | Labour | 0 | 0.0000
329550 | B3 - 3RD FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.012.003. | 0.0000 | Labour | 0 | 0.0000
332024 | B3 - 3RD FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.012.007. | 0.0000 | Labour | 0 | 0.0000
329553 | B3 - 4TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.013.003. | 0.0000 | Labour | 0 | 0.0000
332025 | B3 - 4TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.013.007. | 0.0000 | Labour | 0 | 0.0000
329556 | B3 - 5TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.014.003. | 0.0000 | Labour | 0 | 0.0000
332026 | B3 - 5TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.014.007. | 0.0000 | Labour | 0 | 0.0000
329938 | B3 - 6TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.015.003. | 0.0000 | Labour | 0 | 0.0000
332027 | B3 - 6TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.015.007. | 0.0000 | Labour | 0 | 0.0000
329941 | B3 - 7TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.016.003. | 0.0000 | Labour | 0 | 0.0000
332028 | B3 - 7TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.016.007. | 0.0000 | Labour | 0 | 0.0000
329944 | B3 - 8TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.017.003. | 0.0000 | Labour | 0 | 0.0000
332029 | B3 - 8TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.017.007. | 0.0000 | Labour | 0 | 0.0000
329947 | B3 - 9TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.018.003. | 0.0000 | Labour | 0 | 0.0000
332030 | B3 - 9TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.018.007. | 0.0000 | Labour | 0 | 0.0000
329950 | B3 - 10TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.019.003. | 0.0000 | Labour | 0 | 0.0000
332031 | B3 - 10TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.019.007. | 0.0000 | Labour | 0 | 0.0000
331989 | B3 - 11TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.020.004. | 0.0000 | Labour | 0 | 0.0000
331990 | B3 - 11TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.020.005. | 0.0000 | Labour | 0 | 0.0000
331995 | B3 - 12TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.021.004. | 0.0000 | Labour | 0 | 0.0000
331996 | B3 - 12TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.021.005. | 0.0000 | Labour | 0 | 0.0000
332001 | B3 - 13TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.022.004. | 0.0000 | Labour | 0 | 0.0000
332002 | B3 - 13TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.022.005. | 0.0000 | Labour | 0 | 0.0000
332006 | B3 - 14TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.023.004. | 0.0000 | Labour | 0 | 0.0000
332007 | B3 - 14TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.023.005. | 0.0000 | Labour | 0 | 0.0000
332011 | B3 - 15TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 588.0700 | 588.0700 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.024.004. | 0.0000 | Labour | 0 | 0.0000
332012 | B3 - 15TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 33.9100 | 33.9100 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.024.005. | 0.0000 | Labour | 0 | 0.0000
333701 | B3 - 16TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.9200 | 519.9200 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.025.004. | 0.0000 | Labour | 0 | 0.0000
333707 | B3 - 16TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.1200 | 39.1200 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.025.005. | 0.0000 | Labour | 0 | 0.0000
333702 | B3 - 17TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.9200 | 519.9200 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.026.004. | 0.0000 | Labour | 0 | 0.0000
333708 | B3 - 17TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.1200 | 39.1200 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.026.005. | 0.0000 | Labour | 0 | 0.0000
333703 | B3 - 18TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.9200 | 519.9200 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.027.004. | 0.0000 | Labour | 0 | 0.0000
333709 | B3 - 18TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.1200 | 39.1200 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.027.005. | 0.0000 | Labour | 0 | 0.0000
333704 | B3 - 19TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.9200 | 519.9200 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.028.004. | 0.0000 | Labour | 0 | 0.0000
333710 | B3 - 19TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.1200 | 39.1200 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.028.005. | 0.0000 | Labour | 0 | 0.0000
333705 | B3 - 20TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.9200 | 519.9200 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.029.004. | 0.0000 | Labour | 0 | 0.0000
333711 | B3 - 20TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.1200 | 39.1200 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.029.005. | 0.0000 | Labour | 0 | 0.0000
333706 | B3 - 21ST FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.9200 | 519.9200 | 193 | Labour for Brickbat | Sq.Ft | 519.9200 | 0.0000 | 22.002.004.006.030.004. | 0.0000 | Labour | 0 | 0.0000
333712 | B3 - 21ST FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.1200 | 39.1200 | 193 | Labour for Brickbat | Sq.Ft | 39.1200 | 0.0000 | 22.002.004.006.030.005. | 0.0000 | Labour | 0 | 0.0000