## Sheet1
Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central
Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
329542 | B3 - 1ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.010.001. | 0.0000 | Labour | 0 | 0.0000
329542 | B3 - 1ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.010.001. | 2200.0000 | Labour | 0 | 1585.2300
329545 | B3 - 2ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.011.001. | 0.0000 | Labour | 0 | 0.0000
329545 | B3 - 2ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.011.001. | 2200.0000 | Labour | 0 | 0.0000
329548 | B3 - 3RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.012.001. | 0.0000 | Labour | 0 | 0.0000
329548 | B3 - 3RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.012.001. | 2200.0000 | Labour | 0 | 0.0000
329551 | B3 - 4TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.013.001. | 0.0000 | Labour | 0 | 0.0000
329551 | B3 - 4TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.013.001. | 2200.0000 | Labour | 0 | 0.0000
329554 | B3 - 5TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.014.001. | 0.0000 | Labour | 0 | 0.0000
329554 | B3 - 5TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.014.001. | 2200.0000 | Labour | 0 | 0.0000
329936 | B3 - 6TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.015.001. | 0.0000 | Labour | 0 | 0.0000
329936 | B3 - 6TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2200.0000 | 22.002.004.006.015.001. | 2200.0000 | Labour | 0 | 0.0000
329939 | B3 - 7TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.016.001. | 0.0000 | Labour | 0 | 0.0000
329939 | B3 - 7TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.016.001. | 2200.0000 | Labour | 0 | 0.0000
329942 | B3 - 8TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.017.001. | 0.0000 | Labour | 0 | 0.0000
329942 | B3 - 8TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.017.001. | 2200.0000 | Labour | 0 | 0.0000
329945 | B3 - 9TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.018.001. | 0.0000 | Labour | 0 | 0.0000
329945 | B3 - 9TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.018.001. | 2200.0000 | Labour | 0 | 0.0000
329948 | B3 - 10TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.019.001. | 0.0000 | Labour | 0 | 0.0000
329948 | B3 - 10TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 0.0000 | 22.002.004.006.019.001. | 2200.0000 | Labour | 0 | 0.0000
331988 | B3 - 11TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.020.003. | 0.0000 | Labour | 0 | 0.0000
331988 | B3 - 11TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.020.003. | 2200.0000 | Labour | 0 | 1585.2300
331994 | B3 - 12TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.021.003. | 0.0000 | Labour | 0 | 0.0000
331994 | B3 - 12TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.021.003. | 2200.0000 | Labour | 0 | 1585.2300
332000 | B3 - 13TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.022.003. | 0.0000 | Labour | 0 | 0.0000
332000 | B3 - 13TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.022.003. | 2200.0000 | Labour | 0 | 1585.2300
332005 | B3 - 14TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.023.003. | 0.0000 | Labour | 0 | 0.0000
332005 | B3 - 14TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.023.003. | 2200.0000 | Labour | 0 | 1585.2300
332010 | B3 - 15TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.024.003. | 0.0000 | Labour | 0 | 0.0000
332010 | B3 - 15TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.024.003. | 2200.0000 | Labour | 0 | 1585.2300
333695 | B3 - 16TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.025.003. | 0.0000 | Labour | 0 | 0.0000
333695 | B3 - 16TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.025.003. | 2200.0000 | Labour | 6 | 1585.2200 | C+S GST 18% IP RD
333696 | B3 - 17TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.026.003. | 0.0000 | Labour | 0 | 0.0000
333696 | B3 - 17TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.026.003. | 2200.0000 | Labour | 6 | 1585.2200 | C+S GST 18% IP RD
333697 | B3 - 18TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.027.003. | 0.0000 | Labour | 0 | 0.0000
333697 | B3 - 18TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.027.003. | 2200.0000 | Labour | 6 | 1585.2200 | C+S GST 18% IP RD
333698 | B3 - 19TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.028.003. | 0.0000 | Labour | 0 | 0.0000
333698 | B3 - 19TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.028.003. | 2200.0000 | Labour | 6 | 1585.2200 | C+S GST 18% IP RD
333699 | B3 - 20TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.029.003. | 0.0000 | Labour | 0 | 0.0000
333699 | B3 - 20TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.029.003. | 2200.0000 | Labour | 6 | 1585.2200 | C+S GST 18% IP RD
333700 | B3 - 21ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 271.5646 | 0.0000 | 22.002.004.006.030.003. | 0.0000 | Labour | 0 | 0.0000
333700 | B3 - 21ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.004.006.030.003. | 2200.0000 | Labour | 6 | 1585.2200 | C+S GST 18% IP RD