## Sheet1
Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central
Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
329542 | B3 - 1ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.010.001. | 2200.0000 | Labour | 0 | 1584.0000
329543 | B3 - 1ST FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0000 | 617.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.010.002. | 1600.0000 | Labour | 0 | 0.0000
329545 | B3 - 2ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.011.001. | 2200.0000 | Labour | 0 | 0.0000
329546 | B3 - 2ND FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 569.5900 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 13.0000 | 1600.0000 | 22.002.004.006.011.002. | 1600.0000 | Labour | 0 | 0.0000
329548 | B3 - 3RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.012.001. | 2200.0000 | Labour | 0 | 0.0000
329549 | B3 - 3RD FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0600 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.012.002. | 1600.0000 | Labour | 0 | 0.0000
329551 | B3 - 4TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.013.001. | 2200.0000 | Labour | 0 | 0.0000
329552 | B3 - 4TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0600 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.013.002. | 1600.0000 | Labour | 0 | 0.0000
329554 | B3 - 5TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.014.001. | 2200.0000 | Labour | 0 | 0.0000
329555 | B3 - 5TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0600 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.014.002. | 1600.0000 | Labour | 0 | 0.0000
329936 | B3 - 6TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.015.001. | 2200.0000 | Labour | 0 | 0.0000
329937 | B3 - 6TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0000 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.015.002. | 1600.0000 | Labour | 0 | 0.0000
329939 | B3 - 7TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.016.001. | 2200.0000 | Labour | 0 | 0.0000
329940 | B3 - 7TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 569.5900 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 13.0000 | 1600.0000 | 22.002.004.006.016.002. | 1600.0000 | Labour | 0 | 0.0000
329942 | B3 - 8TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.017.001. | 2200.0000 | Labour | 0 | 0.0000
329943 | B3 - 8TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0600 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.017.002. | 1600.0000 | Labour | 0 | 0.0000
329945 | B3 - 9TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.018.001. | 2200.0000 | Labour | 0 | 0.0000
329946 | B3 - 9TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0600 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.018.002. | 1600.0000 | Labour | 0 | 0.0000
329948 | B3 - 10TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2200.0000 | 22.002.004.006.019.001. | 2200.0000 | Labour | 0 | 0.0000
329949 | B3 - 10TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0600 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.019.002. | 1600.0000 | Labour | 0 | 0.0000
331987 | B3 - 11TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.020.002. | 1600.0000 | Labour | 0 | 0.0000
331988 | B3 - 11TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.020.003. | 2200.0000 | Labour | 0 | 1584.0000
331993 | B3 - 12TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 569.5800 | 569.5800 | 1092 | Labour For Toilet Waterproofing | No. | 13.0000 | 1600.0000 | 22.002.004.006.021.002. | 1600.0000 | Labour | 0 | 0.0000
331994 | B3 - 12TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.021.003. | 2200.0000 | Labour | 0 | 1584.0000
331999 | B3 - 13TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.022.002. | 1600.0000 | Labour | 0 | 0.0000
332000 | B3 - 13TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.022.003. | 2200.0000 | Labour | 0 | 1584.0000
332004 | B3 - 14TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.023.002. | 1600.0000 | Labour | 0 | 0.0000
332005 | B3 - 14TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.023.003. | 2200.0000 | Labour | 0 | 1584.0000
332009 | B3 - 15TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.024.002. | 1600.0000 | Labour | 0 | 0.0000
332010 | B3 - 15TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.024.003. | 2200.0000 | Labour | 0 | 1584.0000
333689 | B3 - 16TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.025.002. | 1600.0000 | Labour | 0 | 0.0000
333695 | B3 - 16TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.025.003. | 2200.0000 | Labour | 0 | 1583.9900
333690 | B3 - 17TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 569.5800 | 569.5800 | 1092 | Labour For Toilet Waterproofing | No. | 13.0000 | 1600.0000 | 22.002.004.006.026.002. | 1600.0000 | Labour | 0 | 0.0000
333696 | B3 - 17TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.026.003. | 2200.0000 | Labour | 0 | 1583.9900
333691 | B3 - 18TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.027.002. | 1600.0000 | Labour | 0 | 0.0000
333697 | B3 - 18TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.027.003. | 2200.0000 | Labour | 0 | 1583.9900
333692 | B3 - 19TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.028.002. | 1600.0000 | Labour | 0 | 0.0000
333698 | B3 - 19TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.028.003. | 2200.0000 | Labour | 0 | 1583.9900
333693 | B3 - 20TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.029.002. | 1600.0000 | Labour | 0 | 0.0000
333699 | B3 - 20TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.029.003. | 2200.0000 | Labour | 0 | 1583.9900
333694 | B3 - 21ST FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.030.002. | 1600.0000 | Labour | 0 | 0.0000
333700 | B3 - 21ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.030.003. | 2200.0000 | Labour | 0 | 1583.9900
333723 | B3 - 22ND FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 569.5800 | 569.5800 | 1092 | Labour For Toilet Waterproofing | No. | 13.0000 | 1600.0000 | 22.002.004.006.031.002. | 1600.0000 | Labour | 0 | 0.0000
333724 | B3 - 22ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.031.003. | 2200.0000 | Labour | 0 | 1583.9900
333730 | B3 - 23RD FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.032.002. | 1600.0000 | Labour | 0 | 0.0000
333731 | B3 - 23RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.032.003. | 2200.0000 | Labour | 0 | 1583.9900
333737 | B3 - 24TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.033.002. | 1600.0000 | Labour | 0 | 0.0000
333738 | B3 - 24TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.033.003. | 2200.0000 | Labour | 0 | 1583.9900
333744 | B3 - 25TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.034.002. | 1600.0000 | Labour | 0 | 0.0000
333745 | B3 - 25TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.034.003. | 2200.0000 | Labour | 0 | 1583.9900
333751 | B3 - 26TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 617.0500 | 617.0500 | 1092 | Labour For Toilet Waterproofing | No. | 14.0000 | 1600.0000 | 22.002.004.006.035.002. | 1600.0000 | Labour | 0 | 0.0000
333752 | B3 - 26TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.035.003. | 2200.0000 | Labour | 0 | 1583.9900
333758 | B3 - 27TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 569.5800 | 569.5800 | 1092 | Labour For Toilet Waterproofing | No. | 13.0000 | 1600.0000 | 22.002.004.006.036.002. | 1600.0000 | Labour | 0 | 0.0000
333759 | B3 - 27TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 124.3200 | 124.3200 | 2379 | Labour For Utility Waterproofing | No. | 4.0000 | 2596.0000 | 22.002.004.006.036.003. | 2200.0000 | Labour | 0 | 1583.9900