## Sheet1
Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central | Project :- Venkatesh Erandawane Central
Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK | Selected Group :- B1 WATERPROOFING WORK
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
330753 | B1 - 1ST FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.009.001. | 0.0000 | Labour | 0 | 0.0000
330753 | B1 - 1ST FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.009.001. | 1600.0000 | Labour | 0 | 0.0000
330754 | B1 - 1ST FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.009.002. | 0.0000 | Labour | 0 | 0.0000
330754 | B1 - 1ST FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.009.002. | 1600.0000 | Labour | 0 | 0.0000
330755 | B1 - 1ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.009.003. | 0.0000 | Labour | 0 | 0.0000
330755 | B1 - 1ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2200.0000 | 22.002.002.006.009.003. | 2200.0000 | Labour | 0 | 0.0000
330756 | B1 - 1ST FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.009.004. | 0.0000 | Labour | 0 | 0.0000
330756 | B1 - 1ST FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2200.0000 | 22.002.002.006.009.004. | 2200.0000 | Labour | 0 | 0.0000
330758 | B1 - 1ST FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.009.006. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
334088 | B1 - 1ST FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.009.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
330759 | B1 - 2ND FLOOR WP CHEMICAL COAT | Sq.Ft | 5434.9000 | 5434.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5467.9 | 8.2600 | 22.002.002.006.010.001. | 7.0000 | Labour | 6 | 6847.9800 | C+S GST 18% IP RD
330761 | B1 - 2ND FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.010.003. | 0.0000 | Labour | 0 | 0.0000
330761 | B1 - 2ND FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.010.003. | 1600.0000 | Labour | 0 | 0.0000
330762 | B1 - 2ND FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.010.004. | 0.0000 | Labour | 0 | 0.0000
330762 | B1 - 2ND FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.010.004. | 1600.0000 | Labour | 0 | 0.0000
330763 | B1 - 2ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.010.005. | 0.0000 | Labour | 0 | 0.0000
330763 | B1 - 2ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2200.0000 | 22.002.002.006.010.005. | 2200.0000 | Labour | 0 | 0.0000
330764 | B1 - 2ND FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.010.006. | 0.0000 | Labour | 0 | 0.0000
330764 | B1 - 2ND FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2200.0000 | 22.002.002.006.010.006. | 2200.0000 | Labour | 0 | 0.0000
334087 | B1 - 2ND FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.010.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
330766 | B1 - 3RD FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.011.002. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
330767 | B1 - 3RD FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.011.003. | 0.0000 | Labour | 0 | 0.0000
330767 | B1 - 3RD FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.011.003. | 1600.0000 | Labour | 0 | 0.0000
330768 | B1 - 3RD FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.011.004. | 0.0000 | Labour | 0 | 0.0000
330768 | B1 - 3RD FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.011.004. | 1600.0000 | Labour | 0 | 0.0000
330769 | B1 - 3RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.011.005. | 0.0000 | Labour | 0 | 0.0000
330769 | B1 - 3RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2200.0000 | 22.002.002.006.011.005. | 2200.0000 | Labour | 0 | 0.0000
330770 | B1 - 3RD FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.011.006. | 0.0000 | Labour | 0 | 0.0000
330770 | B1 - 3RD FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2200.0000 | 22.002.002.006.011.006. | 2200.0000 | Labour | 0 | 0.0000
334086 | B1 - 3RD FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.011.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
330772 | B1 - 4TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.012.002. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
330773 | B1 - 4TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.012.003. | 0.0000 | Labour | 0 | 0.0000
330773 | B1 - 4TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.012.003. | 1600.0000 | Labour | 0 | 0.0000
330774 | B1 - 4TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.012.004. | 0.0000 | Labour | 0 | 0.0000
330774 | B1 - 4TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.012.004. | 1600.0000 | Labour | 0 | 0.0000
330775 | B1 - 4TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.012.005. | 0.0000 | Labour | 0 | 0.0000
330775 | B1 - 4TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2200.0000 | 22.002.002.006.012.005. | 2200.0000 | Labour | 0 | 0.0000
330776 | B1 - 4TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.012.006. | 0.0000 | Labour | 0 | 0.0000
330776 | B1 - 4TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2200.0000 | 22.002.002.006.012.006. | 2200.0000 | Labour | 0 | 0.0000
334085 | B1 - 4TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.012.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
330778 | B1 - 5TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.013.002. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
330779 | B1 - 5TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.013.003. | 0.0000 | Labour | 0 | 0.0000
330779 | B1 - 5TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.013.003. | 1600.0000 | Labour | 0 | 0.0000
330780 | B1 - 5TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.013.004. | 0.0000 | Labour | 0 | 0.0000
330780 | B1 - 5TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 0.0000 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.013.004. | 1600.0000 | Labour | 0 | 0.0000
330781 | B1 - 5TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.013.005. | 0.0000 | Labour | 0 | 0.0000
330781 | B1 - 5TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2200.0000 | 22.002.002.006.013.005. | 2200.0000 | Labour | 0 | 0.0000
330782 | B1 - 5TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.013.006. | 0.0000 | Labour | 0 | 0.0000
330782 | B1 - 5TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 0.0000 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2200.0000 | 22.002.002.006.013.006. | 2200.0000 | Labour | 0 | 0.0000
334084 | B1 - 5TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.013.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
331907 | B1 - 6TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.014.001. | 0.0000 | Labour | 0 | 0.0000
331907 | B1 - 6TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.014.001. | 1600.0000 | Labour | 0 | 0.0000
331910 | B1 - 6TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.014.002. | 0.0000 | Labour | 0 | 0.0000
331910 | B1 - 6TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.014.002. | 1600.0000 | Labour | 0 | 0.0000
331911 | B1 - 6TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.014.003. | 0.0000 | Labour | 0 | 0.0000
331911 | B1 - 6TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.014.003. | 2200.0000 | Labour | 0 | 1584.0000
331912 | B1 - 6TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.014.004. | 0.0000 | Labour | 0 | 0.0000
331912 | B1 - 6TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.014.004. | 2200.0000 | Labour | 0 | 792.0000
331913 | B1 - 6TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.014.005. | 0.0000 | Labour | 0 | 0.0000
331913 | B1 - 6TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.014.005. | 0.0000 | Labour | 0 | 0.0000
331914 | B1 - 6TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.014.006. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
334083 | B1 - 6TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.014.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
331916 | B1 - 7TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.015.001. | 0.0000 | Labour | 0 | 0.0000
331916 | B1 - 7TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.015.001. | 1600.0000 | Labour | 0 | 0.0000
331917 | B1 - 7TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.015.002. | 0.0000 | Labour | 0 | 0.0000
331917 | B1 - 7TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.015.002. | 1600.0000 | Labour | 0 | 0.0000
331918 | B1 - 7TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.015.003. | 0.0000 | Labour | 0 | 0.0000
331918 | B1 - 7TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.015.003. | 2200.0000 | Labour | 0 | 1584.0000
331919 | B1 - 7TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.015.004. | 0.0000 | Labour | 0 | 0.0000
331919 | B1 - 7TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.015.004. | 2200.0000 | Labour | 0 | 792.0000
331920 | B1 - 7TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 408.1100 | 408.1100 | 191 | Labour for Chemical waterproofing | Sq.Ft | 999.1765 | 0.0000 | 22.002.002.006.015.005. | 0.0000 | Labour | 0 | 0.0000
331920 | B1 - 7TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 408.1100 | 408.1100 | 193 | Labour for Brickbat | Sq.Ft | 440.65 | 0.0000 | 22.002.002.006.015.005. | 0.0000 | Labour | 0 | 0.0000
331921 | B1 - 7TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5434.9000 | 5434.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5467.9 | 8.2600 | 22.002.002.006.015.006. | 7.0000 | Labour | 6 | 6847.9800 | C+S GST 18% IP RD
334082 | B1 - 7TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.015.009. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
331923 | B1 - 8TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.016.001. | 0.0000 | Labour | 0 | 0.0000
331923 | B1 - 8TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.016.001. | 1600.0000 | Labour | 0 | 0.0000
331924 | B1 - 8TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.016.002. | 0.0000 | Labour | 0 | 0.0000
331924 | B1 - 8TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.016.002. | 1600.0000 | Labour | 0 | 0.0000
331925 | B1 - 8TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.016.003. | 0.0000 | Labour | 0 | 0.0000
331925 | B1 - 8TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.016.003. | 2200.0000 | Labour | 0 | 1584.0000
331926 | B1 - 8TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.016.004. | 0.0000 | Labour | 0 | 0.0000
331926 | B1 - 8TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.016.004. | 2200.0000 | Labour | 0 | 792.0000
331927 | B1 - 8TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.016.005. | 0.0000 | Labour | 0 | 0.0000
331927 | B1 - 8TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.016.005. | 0.0000 | Labour | 0 | 0.0000
331928 | B1 - 8TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.016.006. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
334081 | B1 - 8TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.016.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
331930 | B1 - 9TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.017.001. | 0.0000 | Labour | 0 | 0.0000
331930 | B1 - 9TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.017.001. | 1600.0000 | Labour | 0 | 0.0000
331931 | B1 - 9TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.017.002. | 0.0000 | Labour | 0 | 0.0000
331931 | B1 - 9TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.017.002. | 1600.0000 | Labour | 0 | 0.0000
331932 | B1 - 9TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.017.003. | 0.0000 | Labour | 0 | 0.0000
331932 | B1 - 9TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.017.003. | 2200.0000 | Labour | 0 | 1584.0000
331933 | B1 - 9TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.017.004. | 0.0000 | Labour | 0 | 0.0000
331933 | B1 - 9TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.017.004. | 2200.0000 | Labour | 0 | 792.0000
331934 | B1 - 9TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.017.005. | 0.0000 | Labour | 0 | 0.0000
331934 | B1 - 9TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.017.005. | 0.0000 | Labour | 0 | 0.0000
331935 | B1 - 9TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.017.006. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
334079 | B1 - 9TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.017.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
331936 | B1 - 10TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.018.001. | 0.0000 | Labour | 0 | 0.0000
331936 | B1 - 10TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 514.0348 | 514.0348 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.018.001. | 1600.0000 | Labour | 0 | 0.0000
331937 | B1 - 10TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.018.002. | 0.0000 | Labour | 0 | 0.0000
331937 | B1 - 10TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8565 | 57.8565 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.018.002. | 1600.0000 | Labour | 0 | 0.0000
331938 | B1 - 10TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.018.003. | 0.0000 | Labour | 0 | 0.0000
331938 | B1 - 10TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 117.0585 | 117.0585 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.018.003. | 2200.0000 | Labour | 0 | 1584.0000
331939 | B1 - 10TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.018.004. | 0.0000 | Labour | 0 | 0.0000
331939 | B1 - 10TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2506 | 54.2506 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.018.004. | 2200.0000 | Labour | 0 | 792.0000
331940 | B1 - 10TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.018.005. | 0.0000 | Labour | 0 | 0.0000
331940 | B1 - 10TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 471.0369 | 471.0369 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.018.005. | 0.0000 | Labour | 0 | 0.0000
331941 | B1 - 10TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.018.006. | 7.0000 | Labour | 6 | 7021.8600 | C+S GST 18% IP RD
334078 | B1 - 10TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.018.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333943 | B1 - 11TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.019.001. | 0.0000 | Labour | 0 | 0.0000
333943 | B1 - 11TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.019.001. | 1600.0000 | Labour | 0 | 0.0000
333944 | B1 - 11TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.019.002. | 0.0000 | Labour | 0 | 0.0000
333944 | B1 - 11TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.019.002. | 1600.0000 | Labour | 0 | 0.0000
333945 | B1 - 11TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.019.003. | 0.0000 | Labour | 0 | 0.0000
333945 | B1 - 11TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.019.003. | 2200.0000 | Labour | 0 | 1584.0000
333946 | B1 - 11TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.019.004. | 0.0000 | Labour | 0 | 0.0000
333946 | B1 - 11TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.019.004. | 2200.0000 | Labour | 0 | 792.0000
333947 | B1 - 11TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.019.005. | 0.0000 | Labour | 0 | 0.0000
333947 | B1 - 11TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.019.005. | 0.0000 | Labour | 0 | 0.0000
333948 | B1 - 11TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.019.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
333956 | B1 - 11TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.019.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333950 | B1 - 12TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.020.001. | 0.0000 | Labour | 0 | 0.0000
333950 | B1 - 12TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.020.001. | 1600.0000 | Labour | 0 | 0.0000
333951 | B1 - 12TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.020.002. | 0.0000 | Labour | 0 | 0.0000
333951 | B1 - 12TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.020.002. | 1600.0000 | Labour | 0 | 0.0000
333952 | B1 - 12TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.020.003. | 0.0000 | Labour | 0 | 0.0000
333952 | B1 - 12TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.020.003. | 2200.0000 | Labour | 0 | 1584.0000
333953 | B1 - 12TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.020.004. | 0.0000 | Labour | 0 | 0.0000
333953 | B1 - 12TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.020.004. | 2200.0000 | Labour | 0 | 792.0000
333954 | B1 - 12TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 191 | Labour for Chemical waterproofing | Sq.Ft | 999.1765 | 0.0000 | 22.002.002.006.020.005. | 0.0000 | Labour | 0 | 0.0000
333954 | B1 - 12TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 193 | Labour for Brickbat | Sq.Ft | 440.65 | 0.0000 | 22.002.002.006.020.005. | 0.0000 | Labour | 0 | 0.0000
333955 | B1 - 12TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5434.9000 | 5434.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5467.9 | 8.2600 | 22.002.002.006.020.006. | 7.0000 | Labour | 6 | 6847.9800 | C+S GST 18% IP RD
333957 | B1 - 12TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.020.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333959 | B1 - 13TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.021.001. | 0.0000 | Labour | 0 | 0.0000
333959 | B1 - 13TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.021.001. | 1600.0000 | Labour | 0 | 0.0000
333960 | B1 - 13TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.021.002. | 0.0000 | Labour | 0 | 0.0000
333960 | B1 - 13TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.021.002. | 1600.0000 | Labour | 0 | 0.0000
333961 | B1 - 13TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.021.003. | 0.0000 | Labour | 0 | 0.0000
333961 | B1 - 13TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.021.003. | 2200.0000 | Labour | 0 | 1584.0000
333962 | B1 - 13TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.021.004. | 0.0000 | Labour | 0 | 0.0000
333962 | B1 - 13TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.021.004. | 2200.0000 | Labour | 0 | 792.0000
333963 | B1 - 13TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.021.005. | 0.0000 | Labour | 0 | 0.0000
333963 | B1 - 13TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.021.005. | 0.0000 | Labour | 0 | 0.0000
333964 | B1 - 13TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.021.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
333965 | B1 - 13TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.021.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333967 | B1 - 14TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.022.001. | 0.0000 | Labour | 0 | 0.0000
333967 | B1 - 14TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.022.001. | 1600.0000 | Labour | 0 | 0.0000
333968 | B1 - 14TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.022.002. | 0.0000 | Labour | 0 | 0.0000
333968 | B1 - 14TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.022.002. | 1600.0000 | Labour | 0 | 0.0000
333969 | B1 - 14TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.022.003. | 0.0000 | Labour | 0 | 0.0000
333969 | B1 - 14TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.022.003. | 2200.0000 | Labour | 0 | 1584.0000
333970 | B1 - 14TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.022.004. | 0.0000 | Labour | 0 | 0.0000
333970 | B1 - 14TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.022.004. | 2200.0000 | Labour | 0 | 792.0000
333971 | B1 - 14TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.022.005. | 0.0000 | Labour | 0 | 0.0000
333971 | B1 - 14TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.022.005. | 0.0000 | Labour | 0 | 0.0000
333972 | B1 - 14TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.022.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
333973 | B1 - 14TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.022.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333975 | B1 - 15TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.023.001. | 0.0000 | Labour | 0 | 0.0000
333975 | B1 - 15TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.023.001. | 1600.0000 | Labour | 0 | 0.0000
333976 | B1 - 15TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.023.002. | 0.0000 | Labour | 0 | 0.0000
333976 | B1 - 15TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.023.002. | 1600.0000 | Labour | 0 | 0.0000
333977 | B1 - 15TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.023.003. | 0.0000 | Labour | 0 | 0.0000
333977 | B1 - 15TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.023.003. | 2200.0000 | Labour | 0 | 1584.0000
333978 | B1 - 15TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.023.004. | 0.0000 | Labour | 0 | 0.0000
333978 | B1 - 15TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.023.004. | 2200.0000 | Labour | 0 | 792.0000
333979 | B1 - 15TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.023.005. | 0.0000 | Labour | 0 | 0.0000
333979 | B1 - 15TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.023.005. | 0.0000 | Labour | 0 | 0.0000
333980 | B1 - 15TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.023.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
333981 | B1 - 15TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.023.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333983 | B1 - 16TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.024.001. | 0.0000 | Labour | 0 | 0.0000
333983 | B1 - 16TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.024.001. | 1600.0000 | Labour | 0 | 0.0000
333984 | B1 - 16TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.024.002. | 0.0000 | Labour | 0 | 0.0000
333984 | B1 - 16TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.024.002. | 1600.0000 | Labour | 0 | 0.0000
333985 | B1 - 16TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.024.003. | 0.0000 | Labour | 0 | 0.0000
333985 | B1 - 16TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.024.003. | 2200.0000 | Labour | 0 | 1584.0000
333986 | B1 - 16TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.024.004. | 0.0000 | Labour | 0 | 0.0000
333986 | B1 - 16TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.024.004. | 2200.0000 | Labour | 0 | 792.0000
333987 | B1 - 16TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.024.005. | 0.0000 | Labour | 0 | 0.0000
333987 | B1 - 16TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.024.005. | 0.0000 | Labour | 0 | 0.0000
333988 | B1 - 16TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.024.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
333989 | B1 - 16TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.024.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333991 | B1 - 17TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.025.001. | 0.0000 | Labour | 0 | 0.0000
333991 | B1 - 17TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.025.001. | 1600.0000 | Labour | 0 | 0.0000
333992 | B1 - 17TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.025.002. | 0.0000 | Labour | 0 | 0.0000
333992 | B1 - 17TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.025.002. | 1600.0000 | Labour | 0 | 0.0000
333993 | B1 - 17TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.025.003. | 0.0000 | Labour | 0 | 0.0000
333993 | B1 - 17TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.025.003. | 2200.0000 | Labour | 0 | 1584.0000
333994 | B1 - 17TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.025.004. | 0.0000 | Labour | 0 | 0.0000
333994 | B1 - 17TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.025.004. | 2200.0000 | Labour | 0 | 792.0000
333995 | B1 - 17TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 191 | Labour for Chemical waterproofing | Sq.Ft | 999.1765 | 0.0000 | 22.002.002.006.025.005. | 0.0000 | Labour | 0 | 0.0000
333995 | B1 - 17TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 193 | Labour for Brickbat | Sq.Ft | 440.65 | 0.0000 | 22.002.002.006.025.005. | 0.0000 | Labour | 0 | 0.0000
333996 | B1 - 17TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5434.9000 | 5434.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5467.9 | 8.2600 | 22.002.002.006.025.006. | 7.0000 | Labour | 6 | 6847.9800 | C+S GST 18% IP RD
333997 | B1 - 17TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.025.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
333999 | B1 - 18TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.026.001. | 0.0000 | Labour | 0 | 0.0000
333999 | B1 - 18TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.026.001. | 1600.0000 | Labour | 0 | 0.0000
334000 | B1 - 18TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.026.002. | 0.0000 | Labour | 0 | 0.0000
334000 | B1 - 18TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.026.002. | 1600.0000 | Labour | 0 | 0.0000
334001 | B1 - 18TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.026.003. | 0.0000 | Labour | 0 | 0.0000
334001 | B1 - 18TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.026.003. | 2200.0000 | Labour | 0 | 1584.0000
334002 | B1 - 18TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.026.004. | 0.0000 | Labour | 0 | 0.0000
334002 | B1 - 18TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.026.004. | 2200.0000 | Labour | 0 | 792.0000
334003 | B1 - 18TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.026.005. | 0.0000 | Labour | 0 | 0.0000
334003 | B1 - 18TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.026.005. | 0.0000 | Labour | 0 | 0.0000
334004 | B1 - 18TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.026.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334005 | B1 - 18TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.026.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334007 | B1 - 19TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.027.001. | 0.0000 | Labour | 0 | 0.0000
334007 | B1 - 19TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.027.001. | 1600.0000 | Labour | 0 | 0.0000
334008 | B1 - 19TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.027.002. | 0.0000 | Labour | 0 | 0.0000
334008 | B1 - 19TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.027.002. | 1600.0000 | Labour | 0 | 0.0000
334009 | B1 - 19TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.027.003. | 0.0000 | Labour | 0 | 0.0000
334009 | B1 - 19TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.027.003. | 2200.0000 | Labour | 0 | 1584.0000
334010 | B1 - 19TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.027.004. | 0.0000 | Labour | 0 | 0.0000
334010 | B1 - 19TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.027.004. | 2200.0000 | Labour | 0 | 792.0000
334011 | B1 - 19TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.027.005. | 0.0000 | Labour | 0 | 0.0000
334011 | B1 - 19TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.027.005. | 0.0000 | Labour | 0 | 0.0000
334012 | B1 - 19TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.027.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334013 | B1 - 19TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.027.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334015 | B1 - 20TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.028.001. | 0.0000 | Labour | 0 | 0.0000
334015 | B1 - 20TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.028.001. | 1600.0000 | Labour | 0 | 0.0000
334016 | B1 - 20TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.028.002. | 0.0000 | Labour | 0 | 0.0000
334016 | B1 - 20TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.028.002. | 1600.0000 | Labour | 0 | 0.0000
334017 | B1 - 20TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.028.003. | 0.0000 | Labour | 0 | 0.0000
334017 | B1 - 20TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.028.003. | 2200.0000 | Labour | 0 | 1584.0000
334018 | B1 - 20TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.028.004. | 0.0000 | Labour | 0 | 0.0000
334018 | B1 - 20TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.028.004. | 2200.0000 | Labour | 0 | 792.0000
334019 | B1 - 20TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.028.005. | 0.0000 | Labour | 0 | 0.0000
334019 | B1 - 20TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.028.005. | 0.0000 | Labour | 0 | 0.0000
334020 | B1 - 20TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.028.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334021 | B1 - 20TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.028.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334023 | B1 - 21ST FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.029.001. | 0.0000 | Labour | 0 | 0.0000
334023 | B1 - 21ST FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.029.001. | 1600.0000 | Labour | 0 | 0.0000
334024 | B1 - 21ST FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.029.002. | 0.0000 | Labour | 0 | 0.0000
334024 | B1 - 21ST FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.029.002. | 1600.0000 | Labour | 0 | 0.0000
334025 | B1 - 21ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.029.003. | 0.0000 | Labour | 0 | 0.0000
334025 | B1 - 21ST FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.029.003. | 2200.0000 | Labour | 0 | 1584.0000
334026 | B1 - 21ST FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.029.004. | 0.0000 | Labour | 0 | 0.0000
334026 | B1 - 21ST FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.029.004. | 2200.0000 | Labour | 0 | 792.0000
334027 | B1 - 21ST FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.029.005. | 0.0000 | Labour | 0 | 0.0000
334027 | B1 - 21ST FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.029.005. | 0.0000 | Labour | 0 | 0.0000
334028 | B1 - 21ST FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.029.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334029 | B1 - 21ST FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.029.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334031 | B1 - 22ND FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.030.001. | 0.0000 | Labour | 0 | 0.0000
334031 | B1 - 22ND FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.030.001. | 1600.0000 | Labour | 0 | 0.0000
334032 | B1 - 22ND FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.030.002. | 0.0000 | Labour | 0 | 0.0000
334032 | B1 - 22ND FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.030.002. | 1600.0000 | Labour | 0 | 0.0000
334033 | B1 - 22ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.030.003. | 0.0000 | Labour | 0 | 0.0000
334033 | B1 - 22ND FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.030.003. | 2200.0000 | Labour | 0 | 1584.0000
334034 | B1 - 22ND FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.030.004. | 0.0000 | Labour | 0 | 0.0000
334034 | B1 - 22ND FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.030.004. | 2200.0000 | Labour | 0 | 792.0000
334035 | B1 - 22ND FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 191 | Labour for Chemical waterproofing | Sq.Ft | 999.1765 | 0.0000 | 22.002.002.006.030.005. | 0.0000 | Labour | 0 | 0.0000
334035 | B1 - 22ND FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 193 | Labour for Brickbat | Sq.Ft | 440.65 | 0.0000 | 22.002.002.006.030.005. | 0.0000 | Labour | 0 | 0.0000
334036 | B1 - 22ND FLOOR WP CHEMICAL COAT | Sq.Ft | 5434.9000 | 5434.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5467.9 | 8.2600 | 22.002.002.006.030.006. | 7.0000 | Labour | 6 | 6847.9800 | C+S GST 18% IP RD
334037 | B1 - 22ND FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.030.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334039 | B1 - 23RD FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.031.001. | 0.0000 | Labour | 0 | 0.0000
334039 | B1 - 23RD FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.031.001. | 1600.0000 | Labour | 0 | 0.0000
334040 | B1 - 23RD FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.031.002. | 0.0000 | Labour | 0 | 0.0000
334040 | B1 - 23RD FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.031.002. | 1600.0000 | Labour | 0 | 0.0000
334041 | B1 - 23RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.031.003. | 0.0000 | Labour | 0 | 0.0000
334041 | B1 - 23RD FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.031.003. | 2200.0000 | Labour | 0 | 1584.0000
334042 | B1 - 23RD FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.031.004. | 0.0000 | Labour | 0 | 0.0000
334042 | B1 - 23RD FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.031.004. | 2200.0000 | Labour | 0 | 792.0000
334043 | B1 - 23RD FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.031.005. | 0.0000 | Labour | 0 | 0.0000
334043 | B1 - 23RD FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.031.005. | 0.0000 | Labour | 0 | 0.0000
334044 | B1 - 23RD FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.031.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334045 | B1 - 23RD FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.031.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334047 | B1 - 24TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.032.001. | 0.0000 | Labour | 0 | 0.0000
334047 | B1 - 24TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.032.001. | 1600.0000 | Labour | 0 | 0.0000
334048 | B1 - 24TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.032.002. | 0.0000 | Labour | 0 | 0.0000
334048 | B1 - 24TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.032.002. | 1600.0000 | Labour | 0 | 0.0000
334049 | B1 - 24TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.032.003. | 0.0000 | Labour | 0 | 0.0000
334049 | B1 - 24TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.032.003. | 2200.0000 | Labour | 0 | 1584.0000
334050 | B1 - 24TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.032.004. | 0.0000 | Labour | 0 | 0.0000
334050 | B1 - 24TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.032.004. | 2200.0000 | Labour | 0 | 792.0000
334051 | B1 - 24TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.032.005. | 0.0000 | Labour | 0 | 0.0000
334051 | B1 - 24TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.032.005. | 0.0000 | Labour | 0 | 0.0000
334052 | B1 - 24TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.032.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334053 | B1 - 24TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.032.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334055 | B1 - 25TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.033.001. | 0.0000 | Labour | 0 | 0.0000
334055 | B1 - 25TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.033.001. | 1600.0000 | Labour | 0 | 0.0000
334056 | B1 - 25TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.033.002. | 0.0000 | Labour | 0 | 0.0000
334056 | B1 - 25TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.033.002. | 1600.0000 | Labour | 0 | 0.0000
334057 | B1 - 25TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.033.003. | 0.0000 | Labour | 0 | 0.0000
334057 | B1 - 25TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.033.003. | 2200.0000 | Labour | 0 | 1584.0000
334058 | B1 - 25TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.033.004. | 0.0000 | Labour | 0 | 0.0000
334058 | B1 - 25TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.033.004. | 2200.0000 | Labour | 0 | 792.0000
334059 | B1 - 25TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.033.005. | 0.0000 | Labour | 0 | 0.0000
334059 | B1 - 25TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.033.005. | 0.0000 | Labour | 0 | 0.0000
334060 | B1 - 25TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.033.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334061 | B1 - 25TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.033.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334063 | B1 - 26TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.034.001. | 0.0000 | Labour | 0 | 0.0000
334063 | B1 - 26TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.034.001. | 1600.0000 | Labour | 0 | 0.0000
334064 | B1 - 26TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.034.002. | 0.0000 | Labour | 0 | 0.0000
334064 | B1 - 26TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.034.002. | 1600.0000 | Labour | 0 | 0.0000
334065 | B1 - 26TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.034.003. | 0.0000 | Labour | 0 | 0.0000
334065 | B1 - 26TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.034.003. | 2200.0000 | Labour | 0 | 1584.0000
334066 | B1 - 26TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.034.004. | 0.0000 | Labour | 0 | 0.0000
334066 | B1 - 26TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.034.004. | 2200.0000 | Labour | 0 | 792.0000
334067 | B1 - 26TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 191 | Labour for Chemical waterproofing | Sq.Ft | 938.2653 | 0.0000 | 22.002.002.006.034.005. | 0.0000 | Labour | 0 | 0.0000
334067 | B1 - 26TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 468.4300 | 468.4300 | 193 | Labour for Brickbat | Sq.Ft | 457.85 | 0.0000 | 22.002.002.006.034.005. | 0.0000 | Labour | 0 | 0.0000
334068 | B1 - 26TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5572.9000 | 5572.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5614.6 | 8.2600 | 22.002.002.006.034.006. | 7.0000 | Labour | 6 | 7021.8500 | C+S GST 18% IP RD
334069 | B1 - 26TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.034.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD
334071 | B1 - 27TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 1089.6978 | 0.0000 | 22.002.002.006.035.001. | 0.0000 | Labour | 0 | 0.0000
334071 | B1 - 27TH FLOOR WP TOILET WP (200MM SUNK) | Sq.Ft | 516.4200 | 516.4200 | 1092 | Labour For Toilet Waterproofing | No. | 14 | 1600.0000 | 22.002.002.006.035.001. | 1600.0000 | Labour | 0 | 0.0000
334072 | B1 - 27TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 191 | Labour for Chemical waterproofing | Sq.Ft | 138.378 | 0.0000 | 22.002.002.006.035.002. | 0.0000 | Labour | 0 | 0.0000
334072 | B1 - 27TH FLOOR WP TOILET WP (250MM SUNK) | Sq.Ft | 57.8600 | 57.8600 | 1092 | Labour For Toilet Waterproofing | No. | 2 | 1600.0000 | 22.002.002.006.035.002. | 1600.0000 | Labour | 0 | 0.0000
334073 | B1 - 27TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 191 | Labour for Chemical waterproofing | Sq.Ft | 257.4941 | 0.0000 | 22.002.002.006.035.003. | 0.0000 | Labour | 0 | 0.0000
334073 | B1 - 27TH FLOOR WP UTILITY WP (150MM SUNK) | Sq.Ft | 120.4200 | 120.4200 | 2379 | Labour For Utility Waterproofing | No. | 4 | 2596.0000 | 22.002.002.006.035.003. | 2200.0000 | Labour | 0 | 1584.0000
334074 | B1 - 27TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 191 | Labour for Chemical waterproofing | Sq.Ft | 135.9505 | 0.0000 | 22.002.002.006.035.004. | 0.0000 | Labour | 0 | 0.0000
334074 | B1 - 27TH FLOOR WP UTILITY WP (250MM SUNK) | Sq.Ft | 54.2500 | 54.2500 | 2379 | Labour For Utility Waterproofing | No. | 2 | 2596.0000 | 22.002.002.006.035.004. | 2200.0000 | Labour | 0 | 792.0000
334075 | B1 - 27TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 191 | Labour for Chemical waterproofing | Sq.Ft | 999.1765 | 0.0000 | 22.002.002.006.035.005. | 0.0000 | Labour | 0 | 0.0000
334075 | B1 - 27TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 498.8400 | 498.8400 | 193 | Labour for Brickbat | Sq.Ft | 440.65 | 0.0000 | 22.002.002.006.035.005. | 0.0000 | Labour | 0 | 0.0000
334076 | B1 - 27TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5434.9000 | 5434.9000 | 2380 | Labour For Chemical Coat W/P | Sq.Ft | 5467.9 | 8.2600 | 22.002.002.006.035.006. | 7.0000 | Labour | 6 | 6847.9800 | C+S GST 18% IP RD
334077 | B1 - 27TH FLOOR WP SLEEVES PACKING | No. | 46.0000 | 46.0000 | 2381 | Labour For Sleevs Hole Packing | No. | 46 | 177.0000 | 22.002.002.006.035.007. | 150.0000 | Labour | 6 | 1242.0000 | C+S GST 18% IP RD