## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
30 | 330916 | B3 - 1ST FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 24 | 329272 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
38 | 330917 | B3 - 2ND FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 32 | 329273 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
46 | 330918 | B3 - 3RD FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 40 | 329274 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
54 | 330919 | B3 - 4TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 48 | 329275 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
62 | 330920 | B3 - 5TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 56 | 329276 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
70 | 330921 | B3 - 6TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 64 | 329277 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
78 | 330922 | B3 - 7TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 72 | 329278 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
86 | 330923 | B3 - 8TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 80 | 329279 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
94 | 330924 | B3 - 9TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 88 | 329280 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
102 | 330925 | B3 - 10TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 96 | 329333 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
105 | 331113 | B3 - 11TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 104 | 329334 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
112 | 331114 | B3 - 12TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 111 | 329335 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
120 | 331115 | B3 - 13TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 119 | 331104 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
127 | 331116 | B3 - 14TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 126 | 331105 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
134 | 331117 | B3 - 15TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 133 | 331106 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
141 | 331118 | B3 - 16TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 140 | 331107 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
144 | 333701 | B3 - 16TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.92 | 519.92 | 140 | 331107 | 4 | 5895 | BALCONY WP (150MM SUNK) | [5 empty] | 0.0000
145 | 333707 | B3 - 16TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.12 | 39.12 | 140 | 331107 | 4 | 5762 | BALCONY WP (450MM SUNK) | [5 empty] | 0.0000
148 | 331119 | B3 - 17TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 147 | 331108 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
151 | 333702 | B3 - 17TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.92 | 519.92 | 147 | 331108 | 4 | 5895 | BALCONY WP (150MM SUNK) | [5 empty] | 0.0000
152 | 333708 | B3 - 17TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.12 | 39.12 | 147 | 331108 | 4 | 5762 | BALCONY WP (450MM SUNK) | [5 empty] | 0.0000
155 | 331120 | B3 - 18TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 154 | 331109 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
158 | 333703 | B3 - 18TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.92 | 519.92 | 154 | 331109 | 4 | 5895 | BALCONY WP (150MM SUNK) | [5 empty] | 0.0000
159 | 333709 | B3 - 18TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.12 | 39.12 | 154 | 331109 | 4 | 5762 | BALCONY WP (450MM SUNK) | [5 empty] | 0.0000
162 | 331121 | B3 - 19TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 161 | 331110 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
165 | 333704 | B3 - 19TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.92 | 519.92 | 161 | 331110 | 4 | 5895 | BALCONY WP (150MM SUNK) | [5 empty] | 0.0000
166 | 333710 | B3 - 19TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.12 | 39.12 | 161 | 331110 | 4 | 5762 | BALCONY WP (450MM SUNK) | [5 empty] | 0.0000
169 | 331122 | B3 - 20TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 168 | 331111 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
172 | 333705 | B3 - 20TH FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.92 | 519.92 | 168 | 331111 | 4 | 5895 | BALCONY WP (150MM SUNK) | [5 empty] | 0.0000
173 | 333711 | B3 - 20TH FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.12 | 39.12 | 168 | 331111 | 4 | 5762 | BALCONY WP (450MM SUNK) | [5 empty] | 0.0000
176 | 331123 | B3 - 21ST FLOOR WP AAC BLOCK FILLING | Sq.Ft | 39.12 | 39.12 | 175 | 331112 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
179 | 333706 | B3 - 21ST FLOOR WP BALCONY WP (150MM SUNK) | Sq.Ft | 519.92 | 519.92 | 175 | 331112 | 4 | 5895 | BALCONY WP (150MM SUNK) | [5 empty] | 0.0000
180 | 333712 | B3 - 21ST FLOOR WP BALCONY WP (450MM SUNK) | Sq.Ft | 39.12 | 39.12 | 175 | 331112 | 4 | 5762 | BALCONY WP (450MM SUNK) | [5 empty] | 0.0000