## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
7 | 329481 | B3 1ST FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 2 | 329343 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
8 | 329482 | B3 1ST FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 2 | 329343 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
32 | 329493 | B3 2ND FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 356.05 | 0.0000 | 27 | 329344 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
33 | 329494 | B3 2ND FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 27 | 329344 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
52 | 329506 | B3 3RD FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 47 | 329345 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
53 | 329507 | B3 3RD FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 47 | 329345 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
72 | 329518 | B3 4TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 67 | 329346 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
73 | 329519 | B3 4TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 67 | 329346 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
93 | 329530 | B3 5TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 88 | 329347 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
94 | 329531 | B3 5TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 88 | 329347 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
114 | 329618 | B3 6TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 109 | 329348 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
115 | 329619 | B3 6TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 109 | 329348 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
134 | 329631 | B3 7TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 356.05 | 0.0000 | 129 | 329349 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
135 | 329632 | B3 7TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 129 | 329349 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
154 | 329644 | B3 8TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 149 | 329350 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
155 | 329645 | B3 8TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 149 | 329350 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
174 | 329657 | B3 9TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 169 | 329351 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
175 | 329658 | B3 9TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 169 | 329351 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
194 | 329670 | B3 10TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 189 | 329352 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
195 | 329671 | B3 10TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 189 | 329352 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
210 | 332682 | B3 11TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 209 | 332596 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
211 | 332683 | B3 11TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 209 | 332596 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
228 | 332699 | B3 12TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 361.7 | 0.0000 | 227 | 332698 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
229 | 332700 | B3 12TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 227 | 332698 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
246 | 332715 | B3 13TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 245 | 332714 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
247 | 332716 | B3 13TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 245 | 332714 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
263 | 332731 | B3 14TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 262 | 332730 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
264 | 332732 | B3 14TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 262 | 332730 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
280 | 332747 | B3 15TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 279 | 332746 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
281 | 332748 | B3 15TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 279 | 332746 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
297 | 332763 | B3 16TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 296 | 332762 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
298 | 332764 | B3 16TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 296 | 332762 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
314 | 332779 | B3 17TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 361.7 | 0.0000 | 313 | 332778 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
315 | 332780 | B3 17TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 313 | 332778 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
331 | 332795 | B3 18TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 330 | 332794 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
332 | 332796 | B3 18TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 330 | 332794 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
348 | 332811 | B3 19TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 347 | 332810 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
349 | 332812 | B3 19TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 347 | 332810 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000
365 | 332827 | B3 20TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.76 | 0.0000 | 364 | 332826 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
366 | 332828 | B3 20TH FLOOR TILING KITCHEN DADO | Sq. Mtr. | 48.74 | 0.0000 | 364 | 332826 | 4 | 5778 | KITCHEN DADO | [5 empty] | 0.0000