## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
17 | 330045 | B3 1ST FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 2 | 329343 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
42 | 330047 | B3 2ND FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 273.2 | 0.0000 | 27 | 329344 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
62 | 330049 | B3 3RD FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 47 | 329345 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
82 | 330051 | B3 4TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 67 | 329346 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
103 | 330053 | B3 5TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 88 | 329347 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
124 | 330055 | B3 6TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 109 | 329348 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
144 | 330057 | B3 7TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 273.2 | 0.0000 | 129 | 329349 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
164 | 330059 | B3 8TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 149 | 329350 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
184 | 330061 | B3 9TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 169 | 329351 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
204 | 330063 | B3 10TH FLOOR TILING DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 189 | 329352 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
221 | 332694 | B3 11TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 209 | 332596 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
222 | 332695 | B3 11TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 209 | 332596 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
239 | 332710 | B3 12TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 227 | 332698 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
240 | 332711 | B3 12TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 273.2 | 0.0000 | 227 | 332698 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
257 | 332726 | B3 13TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 245 | 332714 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
258 | 332727 | B3 13TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 245 | 332714 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
274 | 332742 | B3 14TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 262 | 332730 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
275 | 332743 | B3 14TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 262 | 332730 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
291 | 332758 | B3 15TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 279 | 332746 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
292 | 332759 | B3 15TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 279 | 332746 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
308 | 332774 | B3 16TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 296 | 332762 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
309 | 332775 | B3 16TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 296 | 332762 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
325 | 332790 | B3 17TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 313 | 332778 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
326 | 332791 | B3 17TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 273.2 | 0.0000 | 313 | 332778 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
342 | 332806 | B3 18TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 330 | 332794 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
343 | 332807 | B3 18TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 330 | 332794 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
359 | 332822 | B3 19TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 347 | 332810 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
360 | 332823 | B3 19TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 347 | 332810 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000
376 | 332838 | B3 20TH FLOOR TILING ADHESIVE | Sq. Mtr. | 555.31 | 0.0000 | 364 | 332826 | 4 | 5811 | ADHESIVE | [5 empty] | 0.0000
377 | 332839 | B3 20TH FLOOR TILING B3 DADO ADHESIVE | Sq. Mtr. | 291.08 | 0.0000 | 364 | 332826 | 4 | 5812 | B3 DADO ADHESIVE | [5 empty] | 0.0000