## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
15 | 330815 | B3 GYPSUM - 7TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 14 | 335184 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
17 | 330816 | B3 GYPSUM - 8TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 16 | 335185 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
19 | 330817 | B3 GYPSUM - 9TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 18 | 335186 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
21 | 330818 | B3 GYPSUM - 10TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 20 | 335187 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
23 | 330819 | B3 GYPSUM - 11TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 22 | 335188 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
25 | 332032 | B3 GYPSUM - 12TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 24 | 335189 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
27 | 332033 | B3 GYPSUM - 13TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 26 | 335190 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
29 | 332034 | B3 GYPSUM - 14TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 28 | 335191 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
31 | 332035 | B3 GYPSUM - 15TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 30 | 335192 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
33 | 332373 | B3 GYPSUM - 16TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 32 | 335193 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
35 | 332468 | B3 GYPSUM - 17TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 34 | 335194 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
37 | 332469 | B3 GYPSUM - 18TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 36 | 335195 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
39 | 332470 | B3 GYPSUM - 19TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 38 | 335196 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
41 | 332471 | B3 GYPSUM - 20TH FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 40 | 335197 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
43 | 332472 | B3 GYPSUM - 21ST FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 42 | 335198 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
45 | 332473 | B3 GYPSUM - 22ND FLOOR BOND IT | Sq. Mtr. | 4129.0000 | 4129.0000 | 44 | 335199 | 4 | 5805 | BOND IT | [5 empty] | 0.0000