## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
7 | 329481 | B3 1ST FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 2 | 329343 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
32 | 329493 | B3 2ND FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 356.0500 | 0.0000 | 27 | 329344 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
52 | 329506 | B3 3RD FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 47 | 329345 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
72 | 329518 | B3 4TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 67 | 329346 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
93 | 329530 | B3 5TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 88 | 329347 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
114 | 329618 | B3 6TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 109 | 329348 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
135 | 329631 | B3 7TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 356.0500 | 0.0000 | 130 | 329349 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
156 | 329644 | B3 8TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 151 | 329350 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
177 | 329657 | B3 9TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 172 | 329351 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
198 | 329670 | B3 10TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 193 | 329352 | 4 | 5775 | FLAT FLOORING WORK | [5 empty] | 0.0000
215 | 332682 | B3 11TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 214 | 332596 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
234 | 332699 | B3 12TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 359.42 | 0.0000 | 233 | 332698 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
253 | 332715 | B3 13TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 252 | 332714 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
271 | 332731 | B3 14TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 270 | 332730 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
289 | 332747 | B3 15TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 288 | 332746 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
307 | 332763 | B3 16TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 306 | 332762 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
325 | 332779 | B3 17TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 359.42 | 0.0000 | 324 | 332778 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
343 | 332795 | B3 18TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 342 | 332794 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
361 | 332811 | B3 19TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 360 | 332810 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000
379 | 332827 | B3 20TH FLOOR TILING FLAT FLOORING WORK | Sq. Mtr. | 373.7600 | 0.0000 | 378 | 332826 | 4 | 5351 | FLAT FLOORING WORK | [5 empty] | 0.0000