## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
4 | 329478 | B3 1ST FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 2 | 329343 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
29 | 329490 | B3 2ND FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 27 | 329344 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
49 | 329503 | B3 3RD FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 47 | 329345 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
69 | 329515 | B3 4TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 67 | 329346 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
90 | 329527 | B3 5TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 88 | 329347 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
111 | 329615 | B3 6TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 109 | 329348 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
132 | 329628 | B3 7TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 130 | 329349 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
153 | 329641 | B3 8TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 151 | 329350 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
174 | 329654 | B3 9TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 172 | 329351 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
195 | 329667 | B3 10TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 193 | 329352 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
223 | 332690 | B3 11TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 214 | 332596 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
242 | 332707 | B3 12TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 233 | 332698 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
261 | 332723 | B3 13TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 252 | 332714 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
279 | 332739 | B3 14TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 270 | 332730 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
297 | 332755 | B3 15TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 288 | 332746 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
315 | 332771 | B3 16TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 306 | 332762 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
333 | 332787 | B3 17TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 324 | 332778 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
351 | 332803 | B3 18TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 342 | 332794 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
369 | 332819 | B3 19TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 360 | 332810 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000
387 | 332835 | B3 20TH FLOOR TILING BED TERRACE FLOORING | Sq. Mtr. | 22.39 | 0.0000 | 378 | 332826 | 4 | 5779 | BED TERRACE FLOORING | [5 empty] | 0.0000