## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM | Selected Group :- B1 TYPICAL FLOOR GYPSUM
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
3 | 329023 | B1 GYPSUM - 1ST FLOOR BOND IT | No. | 1962.962 | 1962.962 | 2 | 334140 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
5 | 329024 | B1 GYPSUM - 2ND FLOOR BOND IT | No. | 1972.1 | 1972.1 | 4 | 334141 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
7 | 329025 | B1 GYPSUM - 3RD FLOOR BOND IT | No. | 1962.962 | 1962.962 | 6 | 334142 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
9 | 330804 | B1 GYPSUM - 4TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 8 | 334144 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
11 | 330805 | B1 GYPSUM - 5TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 10 | 334145 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
13 | 330808 | B1 GYPSUM - 6TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 12 | 334146 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
15 | 330809 | B1 GYPSUM - 7TH FLOOR BOND IT | Sq. Mtr. | 1972.1 | 1972.1 | 14 | 334147 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
17 | 334159 | B1 GYPSUM - 8TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 16 | 334160 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
19 | 334161 | B1 GYPSUM - 9TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 18 | 334162 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
21 | 334163 | B1 GYPSUM - 10TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 20 | 334164 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
23 | 334165 | B1 GYPSUM - 11TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 22 | 334166 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
25 | 334167 | B1 GYPSUM - 12TH FLOOR BOND IT | Sq. Mtr. | 1972.1 | 1972.1 | 24 | 334168 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
27 | 334169 | B1 GYPSUM - 13TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 26 | 334170 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
29 | 334171 | B1 GYPSUM - 14TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 28 | 334172 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
31 | 334173 | B1 GYPSUM - 15TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 30 | 334174 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
33 | 334175 | B1 GYPSUM - 16TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 32 | 334176 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
35 | 334177 | B1 GYPSUM - 17TH FLOOR BOND IT | Sq. Mtr. | 1972.1 | 1972.1 | 34 | 334178 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
37 | 334179 | B1 GYPSUM - 18TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 36 | 334180 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
39 | 334181 | B1 GYPSUM - 19TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 38 | 334182 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
41 | 334183 | B1 GYPSUM - 20TH FLOOR BOND IT | Sq. Mtr. | 1962.962 | 1962.962 | 40 | 334184 | 4 | 5805 | BOND IT | [5 empty] | 0.0000