## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK | Selected Group :- B2 WATERPROOFING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
18 | 334089 | B2 - 1ST FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 13 | 329360 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
24 | 334090 | B2 - 2ND FLOOR WP SLEEVES PACKING | No. | 47 | 47 | 19 | 329361 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
30 | 334091 | B2 - 3RD FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 25 | 329362 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
36 | 334092 | B2 - 4TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 31 | 329363 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
42 | 334093 | B2 - 5TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 37 | 329364 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
48 | 334094 | B2 - 6TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 43 | 329365 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
56 | 334095 | B2 - 7TH FLOOR WP SLEEVES PACKING | No. | 47 | 47 | 49 | 329366 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
62 | 334096 | B2 - 8TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 57 | 329367 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
68 | 334097 | B2 - 9TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 63 | 329368 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
74 | 334098 | B2 - 10TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 69 | 329369 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
80 | 334099 | B2 - 11TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 75 | 333856 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
86 | 334100 | B2 - 12TH FLOOR WP SLEEVES PACKING | No. | 47 | 47 | 81 | 333861 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
92 | 334101 | B2 - 13TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 87 | 333866 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
98 | 334102 | B2 - 14TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 93 | 333871 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
104 | 334103 | B2 - 15TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 99 | 333876 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
110 | 334104 | B2 - 16TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 105 | 333881 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
116 | 334105 | B2 - 17TH FLOOR WP SLEEVES PACKING | No. | 47 | 47 | 111 | 333896 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
122 | 334106 | B2 - 18TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 117 | 333886 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
128 | 334107 | B2 - 19TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 123 | 333891 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
134 | 334108 | B2 - 20TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 129 | 333901 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
140 | 334109 | B2 - 21ST FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 135 | 333906 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
146 | 334110 | B2 - 22ND FLOOR WP SLEEVES PACKING | No. | 47 | 47 | 141 | 333911 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
152 | 334111 | B2 - 23RD FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 147 | 333916 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
158 | 334112 | B2 - 24TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 153 | 333921 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
164 | 334113 | B2 - 25TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 159 | 333926 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
170 | 334114 | B2 - 26TH FLOOR WP SLEEVES PACKING | No. | 50 | 50 | 165 | 333931 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
176 | 334115 | B2 - 27TH FLOOR WP SLEEVES PACKING | No. | 47 | 47 | 171 | 333936 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000