## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM | Selected Group :- B3 TYPICAL FLOOR GYPSUM
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
3 | 328767 | B3 GYPSUM - 1ST FLOOR Misc.Work | No. | 1830.55 | 1830.55 | 2 | 335178 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
5 | 329017 | B3 GYPSUM - 2ND FLOOR Misc.Work | No. | 1866.4 | 1866.4 | 4 | 335179 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
7 | 329018 | B3 GYPSUM - 3RD FLOOR Misc.Work | No. | 1830.55 | 1830.55 | 6 | 335180 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
9 | 329019 | B3 GYPSUM - 4TH FLOOR Misc.Work | No. | 1830.55 | 1830.55 | 8 | 335181 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
11 | 329020 | B3 GYPSUM - 5TH FLOOR Misc.Work | No. | 1830.55 | 1830.55 | 10 | 335182 | 4 | 3132 | Misc.Work | [5 empty] | 0.0000
13 | 330814 | B3 GYPSUM - 6TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 12 | 335183 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
15 | 330815 | B3 GYPSUM - 7TH FLOOR BOND IT | Sq. Mtr. | 1866.4 | 1866.4 | 14 | 335184 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
17 | 330816 | B3 GYPSUM - 8TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 16 | 335185 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
19 | 330817 | B3 GYPSUM - 9TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 18 | 335186 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
21 | 330818 | B3 GYPSUM - 10TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 20 | 335187 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
23 | 330819 | B3 GYPSUM - 11TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 22 | 335188 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
25 | 332032 | B3 GYPSUM - 12TH FLOOR BOND IT | Sq. Mtr. | 1866.4 | 1866.4 | 24 | 335189 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
27 | 332033 | B3 GYPSUM - 13TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 26 | 335190 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
29 | 332034 | B3 GYPSUM - 14TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 28 | 335191 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
31 | 332035 | B3 GYPSUM - 15TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 30 | 335192 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
33 | 332373 | B3 GYPSUM - 16TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 32 | 335193 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
35 | 332468 | B3 GYPSUM - 17TH FLOOR BOND IT | Sq. Mtr. | 1866.4 | 1866.4 | 34 | 335194 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
37 | 332469 | B3 GYPSUM - 18TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 36 | 335195 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
39 | 332470 | B3 GYPSUM - 19TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 38 | 335196 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
41 | 332471 | B3 GYPSUM - 20TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 40 | 335197 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
43 | 332472 | B3 GYPSUM - 21ST FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 42 | 335198 | 4 | 5805 | BOND IT |  |  |  |  | Started | 0.0000
45 | 332473 | B3 GYPSUM - 22ND FLOOR BOND IT | Sq. Mtr. | 1866.4 | 1866.4 | 44 | 335199 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
47 | 336115 | B3 GYPSUM - 23RD FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 46 | 336108 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
49 | 336116 | B3 GYPSUM - 24TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 48 | 336109 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
51 | 336117 | B3 GYPSUM - 25TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 50 | 336110 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
53 | 336118 | B3 GYPSUM - 26TH FLOOR BOND IT | Sq. Mtr. | 1830.55 | 1830.55 | 52 | 336111 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
55 | 336119 | B3 GYPSUM - 27TH FLOOR BOND IT | Sq. Mtr. | 1866.4 | 1866.4 | 54 | 336112 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
57 | 336120 | B3 GYPSUM - 28TH FLOOR BOND IT | Sq. Mtr. | 1654.8 | 1654.8 | 56 | 336113 | 4 | 5805 | BOND IT | [5 empty] | 0.0000
59 | 336121 | B3 GYPSUM - 29TH FLOOR BOND IT | Sq. Mtr. | 1617.8 | 1617.8 | 58 | 336114 | 4 | 5805 | BOND IT | [5 empty] | 0.0000