## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK | Selected Group :- B3 WATERPROOFING WORK
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
27 | 329976 | B3 - 1ST FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 23 | 329272 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
28 | 330733 | B3 - 1ST FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 23 | 329272 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
29 | 330916 | B3 - 1ST FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 23 | 329272 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
35 | 329977 | B3 - 2ND FLOOR WP CHEMICAL COAT | Sq.Ft | 4881 | 4881 | 31 | 329273 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
36 | 330734 | B3 - 2ND FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 31 | 329273 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
37 | 330917 | B3 - 2ND FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 31 | 329273 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
43 | 329978 | B3 - 3RD FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 39 | 329274 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
44 | 330735 | B3 - 3RD FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 39 | 329274 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
45 | 330918 | B3 - 3RD FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 39 | 329274 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
51 | 329979 | B3 - 4TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 47 | 329275 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
52 | 330736 | B3 - 4TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 47 | 329275 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
53 | 330919 | B3 - 4TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 47 | 329275 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
59 | 329980 | B3 - 5TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 55 | 329276 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
60 | 330737 | B3 - 5TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 55 | 329276 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
61 | 330920 | B3 - 5TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 55 | 329276 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
67 | 329981 | B3 - 6TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 63 | 329277 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
68 | 330738 | B3 - 6TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 63 | 329277 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
69 | 330921 | B3 - 6TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 63 | 329277 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
75 | 329982 | B3 - 7TH FLOOR WP CHEMICAL COAT | Sq.Ft | 4881 | 4881 | 71 | 329278 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
76 | 330739 | B3 - 7TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 71 | 329278 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
77 | 330922 | B3 - 7TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 71 | 329278 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
83 | 329983 | B3 - 8TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 79 | 329279 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
84 | 330740 | B3 - 8TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 79 | 329279 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
85 | 330923 | B3 - 8TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 79 | 329279 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
91 | 329984 | B3 - 9TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 87 | 329280 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
92 | 330741 | B3 - 9TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 87 | 329280 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
93 | 330924 | B3 - 9TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 87 | 329280 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
99 | 329985 | B3 - 10TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 95 | 329333 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
100 | 330742 | B3 - 10TH FLOOR WP SLEEVES PACKING | No. | 40 | 40 | 95 | 329333 | 4 | 5828 | SLEEVES PACKING | [5 empty] | 0.0000
101 | 330925 | B3 - 10TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 95 | 329333 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
104 | 331113 | B3 - 11TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 103 | 329334 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
109 | 331992 | B3 - 11TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 103 | 329334 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
111 | 331114 | B3 - 12TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 110 | 329335 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
117 | 331998 | B3 - 12TH FLOOR WP CHEMICAL COAT | Sq.Ft | 4881 | 4881 | 110 | 329335 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
119 | 331115 | B3 - 13TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 118 | 331104 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
124 | 332003 | B3 - 13TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 118 | 331104 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
126 | 331116 | B3 - 14TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 125 | 331105 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
131 | 332008 | B3 - 14TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 125 | 331105 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
133 | 331117 | B3 - 15TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 132 | 331106 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
138 | 332013 | B3 - 15TH FLOOR WP CHEMICAL COAT | Sq.Ft | 5095 | 5095 | 132 | 331106 | 4 | 5806 | CHEMICAL COAT | [5 empty] | 0.0000
140 | 331118 | B3 - 16TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 139 | 331107 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
142 | 331119 | B3 - 17TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 141 | 331108 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
144 | 331120 | B3 - 18TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 143 | 331109 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
146 | 331121 | B3 - 19TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 145 | 331110 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
148 | 331122 | B3 - 20TH FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 147 | 331111 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000
150 | 331123 | B3 - 21ST FLOOR WP AAC BLOCK FILLING | Sq.Ft | 35.71 | 35.71 | 149 | 331112 | 4 | 5845 | AAC BLOCK FILLING | [5 empty] | 0.0000