## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING | Selected Group :- B1 TILING
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
29 | 331858 | B1 1ST FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 12 | 329416 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
49 | 331859 | B1 2ND FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 545.79 | 32 | 329417 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
69 | 331860 | B1 3RD FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 52 | 329418 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
89 | 331861 | B1 4TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 72 | 329419 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
109 | 331862 | B1 5TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 92 | 329420 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
126 | 331863 | B1 6TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 112 | 329421 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
197 | 332860 | B1 11TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 184 | 332843 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
212 | 332875 | B1 12TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 545.79 | 199 | 332862 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
227 | 332890 | B1 13TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 214 | 332877 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
242 | 332905 | B1 14TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 229 | 332892 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
257 | 332920 | B1 15TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 244 | 332907 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
272 | 332935 | B1 16TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 259 | 332922 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
287 | 332950 | B1 17TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 545.79 | 274 | 332937 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
302 | 333443 | B1 18TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 289 | 333430 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
317 | 333458 | B1 19TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 304 | 333445 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
332 | 333473 | B1 16TH FLOOR TILING SCREED WORK | Sq. Mtr. | 564.33 | 564.33 | 319 | 333460 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000