## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK | Selected Group :- B1 ALU. WORK / GLASS WORK
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 338112 | B1 ALU. WORK / GLASS WORK | Doz. | 0.0000 | 0.0000 | 0 | 277323 | 31 | 0 | [6 empty] | 0.0000
2 | 338113 | B1- ENTRANCE LOBBY | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
3 | 338115 | B1 1ST FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 |  | Building |  |  |  |  | 0.0000
4 | 338139 | B1 1ST FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 3 | 338115 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
5 | 338117 | B1 2ND FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
6 | 338119 | B1 2ND FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 5 | 338117 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
7 | 338118 | B1 3RD FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
8 | 338120 | B1 3RD FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 7 | 338118 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
9 | 338121 | B1 4TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
10 | 338122 | B1 4TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 9 | 338121 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
11 | 338123 | B1 5TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
12 | 338124 | B1 5TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 11 | 338123 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
13 | 338125 | B1 6TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
14 | 338126 | B1 6TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 13 | 338125 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
15 | 338127 | B1 7TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
16 | 338128 | B1 7TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 15 | 338127 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
17 | 338129 | B1 8TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
18 | 338130 | B1 8TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 17 | 338129 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
19 | 338131 | B1 9TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
20 | 338132 | B1 9TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 19 | 338131 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
21 | 338133 | B1 10TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
22 | 338134 | B1 10TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 21 | 338133 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
23 | 338135 | B1 11TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
24 | 338136 | B1 11TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 23 | 338135 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000
25 | 338137 | B1 12TH FLOOR | Doz. | 0.0000 | 0.0000 | 1 | 338112 | 31 | 0 | [6 empty] | 0.0000
26 | 338138 | B1 12TH FLOOR SLIDING DOOR WINDOW | Sq.Ft | 1000 | 1000 | 25 | 338137 | 4 | 6207 | SLIDING DOOR WINDOW | [5 empty] | 0.0000