## Sheet1
Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central | Project :-Venkatesh Erandawane Central
Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING | Selected Group :- B3 TYPICAL FLOOR TILING
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
104 | 331050 | B3 5TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 0.0000 | 88 | 329347 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
125 | 331051 | B3 6TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 0.0000 | 109 | 329348 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
146 | 331052 | B3 7TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 519.0000 | 0.0000 | 130 | 329349 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
169 | 334218 | B3 8TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 151 | 329350 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
190 | 334219 | B3 9TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 172 | 329351 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
211 | 334220 | B3 10TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 193 | 329352 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
230 | 334221 | B3 11TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 214 | 332596 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
249 | 334222 | B3 12TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 519.0000 | 519.0000 | 233 | 332698 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
268 | 334224 | B3 13TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 252 | 332714 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
287 | 334225 | B3 14TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 271 | 332730 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
306 | 334226 | B3 15TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 290 | 332746 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
325 | 334227 | B3 16TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 309 | 332762 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
344 | 334223 | B3 17TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 519.0000 | 519.0000 | 328 | 332778 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
363 | 334228 | B3 18TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 347 | 332794 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
382 | 334229 | B3 19TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 366 | 332810 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
401 | 334230 | B3 20TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 385 | 332826 | 4 | 5856 | 30 MM SCREED WORK | [5 empty] | 0.0000
420 | 337000 | B3 21ST FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 404 | 336984 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000
439 | 337019 | B3 22ND FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 519.0000 | 519.0000 | 423 | 337003 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000
458 | 337038 | B3 23RD FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 442 | 337022 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000
477 | 337057 | B3 24TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 461 | 337041 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000
496 | 337076 | B3 25TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 480 | 337060 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000
515 | 337095 | B3 26TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 540.0000 | 540.0000 | 499 | 337079 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000
534 | 337114 | B3 27TH FLOOR TILING 50 MM SCREED WORK | Sq. Mtr. | 519.0000 | 519.0000 | 518 | 337098 | 4 | 5856 | 30 MM SCREED WORK |  |  |  |  | Started | 0.0000