## Sheet1
Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI
Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
25 | 335913 | B-2ND FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 21 | 334548 | 4 | 6043 | Flat Flooring | [5 empty] | 0.0000
38 | 335931 | B-3RD FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 36 | 335681 | 4 | 6043 | Flat Flooring | [5 empty] | 0.0000
51 | 336019 | B-4TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 49 | 335682 | 4 | 6043 | Flat Flooring | [5 empty] | 0.0000
64 | 336255 | B-5TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 62 | 336253 | 4 | 6043 | Flat Flooring |  |  |  |  | Started | 0.0000
77 | 336326 | B-6TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 75 | 336324 | 4 | 6043 | Flat Flooring |  |  |  |  | Started | 0.0000
90 | 338322 | B-7TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 88 | 338320 | 4 | 6043 | Flat Flooring |  |  |  |  | Started | 0.0000
103 | 338335 | B-8TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 101 | 338333 | 4 | 6043 | Flat Flooring | [5 empty] | 0.0000
116 | 338348 | B-9TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 209.77 | 0.0000 | 114 | 338346 | 4 | 6043 | Flat Flooring | [5 empty] | 0.0000
129 | 338361 | B-10TH FLOOR TILING WORK Flat Flooring | Sq. Mtr. | 212.91 | 0.0000 | 127 | 338359 | 4 | 6043 | Flat Flooring | [5 empty] | 0.0000