## Sheet1
Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI
Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
26 | 335914 | B-2ND FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 21 | 334548 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
28 | 335916 | B-2ND FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 21 | 334548 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000
39 | 335932 | B-3RD FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 36 | 335681 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
42 | 335935 | B-3RD FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 36 | 335681 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000
52 | 336020 | B-4TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 49 | 335682 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
54 | 336022 | B-4TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 49 | 335682 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000
65 | 336256 | B-5TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 62 | 336253 | 4 | 6045 | Comman Toilet Flooring |  |  |  |  | Started | 0.0000
67 | 336258 | B-5TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 62 | 336253 | 4 | 6047 | Master Toilet Flooring |  |  |  |  | Started | 0.0000
78 | 336327 | B-6TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 75 | 336324 | 4 | 6045 | Comman Toilet Flooring |  |  |  |  | Started | 0.0000
80 | 336329 | B-6TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 75 | 336324 | 4 | 6047 | Master Toilet Flooring |  |  |  |  | Started | 0.0000
91 | 338323 | B-7TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 88 | 338320 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
93 | 338325 | B-7TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 88 | 338320 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000
104 | 338336 | B-8TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 101 | 338333 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
106 | 338338 | B-8TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 101 | 338333 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000
117 | 338349 | B-9TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 114 | 338346 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
119 | 338351 | B-9TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 114 | 338346 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000
130 | 338362 | B-10TH FLOOR TILING WORK Comman Toilet Flooring | Sq. Mtr. | 11.22 | 0.0000 | 127 | 338359 | 4 | 6045 | Comman Toilet Flooring | [5 empty] | 0.0000
132 | 338364 | B-10TH FLOOR TILING WORK Master Toilet Flooring | Sq. Mtr. | 12.99 | 0.0000 | 127 | 338359 | 4 | 6047 | Master Toilet Flooring | [5 empty] | 0.0000