## Sheet1
Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI
Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
9 | 334429 | B-1ST FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 24.36 | 0.0000 | 5 | 333719 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
27 | 335915 | B-2ND FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 21 | 334548 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
29 | 335917 | B-2ND FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 21 | 334548 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
40 | 335933 | B-3RD FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 36 | 335681 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
41 | 335934 | B-3RD FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 36 | 335681 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
53 | 336021 | B-4TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 49 | 335682 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
55 | 336023 | B-4TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 49 | 335682 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
66 | 336257 | B-5TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 62 | 336253 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
68 | 336259 | B-5TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 62 | 336253 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
79 | 336328 | B-6TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 75 | 336324 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
81 | 336330 | B-6TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 75 | 336324 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
92 | 338324 | B-7TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 88 | 338320 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
94 | 338326 | B-7TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 88 | 338320 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
105 | 338337 | B-8TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 101 | 338333 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
107 | 338339 | B-8TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 101 | 338333 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
118 | 338350 | B-9TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 114 | 338346 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
120 | 338352 | B-9TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 114 | 338346 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000
131 | 338363 | B-10TH FLOOR TILING WORK Comman Toilet Dado | Sq. Mtr. | 49.76 | 0.0000 | 127 | 338359 | 4 | 6044 | Comman Toilet Dado | [5 empty] | 0.0000
133 | 338365 | B-10TH FLOOR TILING WORK Master Toilet Dado | Sq. Mtr. | 57.01 | 0.0000 | 127 | 338359 | 4 | 6046 | Master Toilet Dado | [5 empty] | 0.0000