## Sheet1
Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI
Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
14 | 334434 | B-1ST FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 6.47 | 0.0000 | 5 | 333719 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
30 | 335918 | B-2ND FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 21 | 334548 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
31 | 335919 | B-2ND FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 21 | 334548 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000
43 | 335936 | B-3RD FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 36 | 335681 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
44 | 335937 | B-3RD FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 36 | 335681 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000
56 | 336024 | B-4TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 49 | 335682 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
57 | 336025 | B-4TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 49 | 335682 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000
69 | 336260 | B-5TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 62 | 336253 | 4 | 6049 | Utility Flooring |  |  |  |  | Started | 0.0000
70 | 336261 | B-5TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 62 | 336253 | 4 | 6163 | Utility Dado |  |  |  |  | Started | 0.0000
82 | 336331 | B-6TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 75 | 336324 | 4 | 6049 | Utility Flooring |  |  |  |  | Started | 0.0000
83 | 336332 | B-6TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 75 | 336324 | 4 | 6163 | Utility Dado |  |  |  |  | Started | 0.0000
95 | 338327 | B-7TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 88 | 338320 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
96 | 338328 | B-7TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 88 | 338320 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000
108 | 338340 | B-8TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 101 | 338333 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
109 | 338341 | B-8TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 101 | 338333 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000
121 | 338353 | B-9TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 114 | 338346 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
122 | 338354 | B-9TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 114 | 338346 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000
134 | 338366 | B-10TH FLOOR TILING WORK Utility Flooring | Sq. Mtr. | 10.46 | 0.0000 | 127 | 338359 | 4 | 6049 | Utility Flooring | [5 empty] | 0.0000
135 | 338367 | B-10TH FLOOR TILING WORK Utility Dado | Sq. Mtr. | 19.19 | 0.0000 | 127 | 338359 | 4 | 6163 | Utility Dado | [5 empty] | 0.0000