## Sheet1
Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI | Project :-VENKATESH ANANDMAYI
Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK | Selected Group :- B-FLOORING AND TILING WORK
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
8 | 334410 | B-1ST FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.11 | 0.0000 | 5 | 333719 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
17 | 334564 | B-1ST FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 19.11 | 0.0000 | 5 | 333719 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
32 | 335920 | B-2ND FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 21 | 334548 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
33 | 335921 | B-2ND FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 21 | 334548 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
45 | 335938 | B-3RD FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 36 | 335681 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
46 | 335939 | B-3RD FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 36 | 335681 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
58 | 336026 | B-4TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 49 | 335682 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
59 | 336027 | B-4TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 49 | 335682 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
71 | 336262 | B-5TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 62 | 336253 | 4 | 6048 | Balcony flooring |  |  |  |  | Started | 0.0000
72 | 336263 | B-5TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 62 | 336253 | 4 | 6202 | Kitchen Dado |  |  |  |  | Started | 0.0000
84 | 336333 | B-6TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 75 | 336324 | 4 | 6048 | Balcony flooring |  |  |  |  | Started | 0.0000
85 | 336334 | B-6TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 75 | 336324 | 4 | 6202 | Kitchen Dado |  |  |  |  | Started | 0.0000
97 | 338329 | B-7TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 88 | 338320 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
98 | 338330 | B-7TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 88 | 338320 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
110 | 338342 | B-8TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 101 | 338333 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
111 | 338343 | B-8TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 101 | 338333 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
123 | 338355 | B-9TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 114 | 338346 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
124 | 338356 | B-9TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 114 | 338346 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000
136 | 338368 | B-10TH FLOOR TILING WORK Balcony flooring | Sq. Mtr. | 22.49 | 0.0000 | 127 | 338359 | 4 | 6048 | Balcony flooring | [5 empty] | 0.0000
137 | 338369 | B-10TH FLOOR TILING WORK Kitchen Dado | Sq. Mtr. | 34.38 | 0.0000 | 127 | 338359 | 4 | 6202 | Kitchen Dado | [5 empty] | 0.0000